## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 16
PROJECT NAME | Indian Language Sentence Completion
PROJECT MENTOR (sponsor) | Chaitanya Sagar
TEAM MEMBERS | Priet Ukani
Garvit Gupta
Shreyansh
Siddharth Agarwal

## Status
PROJECT NUMBER | 16
PROJECT NAME | Indian Language Sentence Completion
PROJECT MENTOR (sponsor) | Chaitanya Sagar
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting 1 with client (17-1-24) | Coordination | Bhav Beri | 4 | 4 | Done | Introduction to client and project | 0 | 0
GIT Repository setup | Preparation | Siddharth | 0.25 | 0.25 | Done |  | 0 | 0
Referring resources | Preparation | All | 4 | 6 | Done | 1. Build & Publish a Custom Google Chrome Extension - https://www.youtube.com/watch?v=wHZCYi1K664&t=819s 2. Extension which can analyze text - https://itnext.io/how-to-build-a-chrome-extension-to-analyze-text-as-you-write-a1c0ab1923f9 3. Creating a Chrome Extension - https://scribehow.com/library/how-to-create-a-chrome-extension
Fix meeting 2 with client (19-1-24) | Coordination | Dharmik S | 4 | 2 | Done | Intro to NLP backend | 2 | 100
Joining Slack for communication | Preparation | All | 0.25 | 0.25 | Done |  | 0 | 0
Status tracker | Documentation | All | 1 | 0.5 | Done |  | 0.5 | 100
Week 2 (January 22 - January 28)
Fix meeting 3 with client (24-1-24) | Coordination | Dharmik S | 4 | 3 | Done | Deciding on frameworks, architecture and schedule | 1 | 33.3333
Status tracker | Documentation | All | 1 | 0.5 | Done |  | 0.5 | 100
Project synopsis writeup | Documentation | All | 2 | 1 | Done |  | 1 | 100
Fix Meeting 4 with client(25-1-24) | Coordination | Dharmik S | 1 | 0 | Delayed | Timeline and Architecture PPT , Mission Statement | 1
Week 3 (January 29 - February 4)
Collecting resources and working on tasks for 02-02 Meeting | Requirements | Siddharth, Shreyansh | 6 | 8 | Done |  | -2 | 25
Making Presentation for 02-02 Meeting | Preparation | Garvit, Priet | 2 | 2 | Done | Presentation consisting various possible architectures to deploy model on cloud | 0 | 0
Fix Meeting with client (02-02-2024) | Coordination | Dharmik S | 2 | 2 | Done | Presenting diff cloud models, Future task- to add more on GCP | 0 | 0
Google Cloud Estimates | Requirements | Siddharth, Shreyansh | 1 | 2 | Done | Getting proper pricing as per requirements | -1 | 50
Status_Tracker, MoM for previous meeting | Documentation | Priet | 0.5 | 0.5 | Done |  | 0 | 0
Updating presentation for 05-02 meeting | Preparation | All | 1 | 1 | Done | Included different price estimates for GCP | 0 | 0
Week 4 ( February 5 - February 11)
Fix Meeting with client (05-02-2024) at 5:10 pm | Coordination | Dharmik S | 2 | 2 | Delayed | Company CEO is busy | 0 | 0
Fix Meeting with client (06-02-2024) at 2:00 pm | Coordination | Dharmik S | 2 | 2 | Done | Meet with CEO. (CEO reviewed architecture and asked to search for proof supporting the architecture) | 0 | 0
Making Presentation for 09-02 Meeting | Preparation | Siddharth,Shreyansh | 2 | 2 | Done | Presenting documentation of use of AWS in industry | 0 | 0
Fix Meeting with client (09-02-2024) | Coordination | Dharmik S | 2 | 1 | Done | Grammarly uses lambda ( Proof given to clients) | 1 | 100
Week 5 (February 12 - February 18)
MoM for previous meetings | Documentation | Shreyansh, Siddharth | 0.25 | 0.25 | Done |  | 0 | 0
Status_Tracker | Documentation | Siddharth, Shreyansh | 0.5 | 0.5 | Done |  | 0 | 0
Discussion about various architectures | Preparation | All | 6 | 8 | Done | Discuss characteristics about different architetures like latency | -2 | 25
Fix Meeting with client (13-02-2024) | Coordination | Dharmik S | 2 | 2 | Done | Further discussion about possible cloud architecture | 0 | 0
MoM for previous meeting | Documentation | Siddharth,Shreyansh | 0.25 | 0.25 | Done
Status_Tracker | Documentation | Shreyansh, Siddharth | 0.5 | 0.5 | Done
Difference between various architectures | Preparation | All | 3 | 2 | Done | Discuss differences between different architectures
Fix meeting with client (16-02-2024) | Coordination | All | 2 | 2 | Done | Presented a brief comparison among cloud architectures services.
SRS Document (By 18-02-2024) | Documentation | All | 4 | 4 | Done | Documentation for requirements
Final Cloud Service Model PPT | Documentation | All | 6 | 4 | Done | Have to write results after testing NLP model on cloud services.
Status_Tracker | Documentation | Garvit | 0.5 | 0.5 | Done |  | 0 | 0
Week 6 (February 19 - February 25)
Test Plan Tracker(By 22-02-2024) | Documentation | All | 6 | 8 | Done | Documentation for test plans for extension | -2 | 25
Fix meeting with client (21-02-2024) | Coordination | All | 2 | 2 | Done | No update from client side about AWS | 0 | 0
Testing NLP model on cloud Services | Preparation | All | 6 | 0 | Delayed | Delay from client side | 6
Activating company cloud service | Coordination | All | 2 | 0 | Delayed | Delay from client side | 2
Fix meeting with client (22/23-02-2024) | Coordination | All | 2 | 0 | Delayed | Delay from client side | 2
MoM for 21-02-2024 | Documentation | Priet | 0.25 | 0.25 | Done | No update from client side regarding AWS | 0 | 0
Week 7 (February 26 - March 3)
Fix meeting with client(01-03-2024) | Coordination | All | 2 | 0 | Delayed | Delay from client side | 2
Week 8 (March 4 - March 10)
Fix meeting with client(04-03-2024) | Coordination | All | 2 | 2 | Done | Review of deployed model on colab and design discussion | 0 | 0
Mock API bw colab server & client | Development | All | 4 | 10 | Done | Deployed Model on Colab and established connection | -6 | 60
Fix meeting with client(06-03-2024) | Coordination | All | 2 | 2 | Done | Review of possible designs for chrome extension
UI component’s Design | Design | All | 4 | 4 | Done | Find some UI component’s design and suggest to client
MOM for Meeting on (04-03-2024) | Documentation | Garvit | 1 | 0.5 | Done
Main Menu Design | Design | All | 4 | 4 | Done | Send Main Menu Design to Client
MOM for meeting on (06-03-2024) | Documentation | Garvit | 0.25 | 0.25 | Done
Status tracker | Documentation | Shreyansh, Siddharth | 1 | 1 | Done
Implementation of Extension(input monitoring & fetching along with basic design of chrome extension) | Development | All | 20 | 16 | Done | Still more Perfection can be done after R1,
Figma design of settings page | Development | Garvit, Priet | 2 | 2 | Done | Prototype of Figma Design of Main Menu
Reworking on client inputs of Figma design | Development | Garvit, Priet | 2 | 1 | Done | Changing based on user input
Fix meeting with client(09-03-2024) | Coordination | All | 2 | 0 | Delayed | Meeting cancelled as client busy
Integration of Server with JS | Development | All | 16 | 16 | Done | To integrate the temporary Cloud server with JS code to give outputs based on user input
Telugu Text detection | Development | All | 6 | 6 | Done | To detect Telugu text and only give output from server if Telugun is found
Week 9 (March 11 - March 17)
Design Document (11-03-2024) | Documentation | All | 4 | 4 | Done | UML design for extension V1 | 0 | 0
Fix meeting with client(11-03-2024) | Coordination | All | 3 | 0 | Delayed | Postponed to 12-03-2024 due to DASS paper showing | 3
Fix meeting with client(12-03-2024) | Coordination | All | 2 | 1 | Done | Quick catchup to tell about DigitalOcean cloud services
MoM for meeting on (12-03-2024) | Coordination | All | 0.5 | 0.5 | Done | Start development now, Figma finalised
Showing Output of responses got from server | Development | All | 24 | 30 | Done | It is working for specific fields | -6 | 20
Reworking on SRS and Project Plan Docs | Documentation | All | 4 | 4 | Done | Modifying the requirements and plan | 0 | 0
Week 10 (March 18 - March 24)
Fix meeting with client(19-03-2024) | Coordination | All | 2 | 2 | Done | Presented first draft of extension | 0 | 0
Perfecting extension for Gmail website | Development | All | 12 | 12 | Done | Handeling issues of extension on gmail website | 0 | 0
Video recording of working extension for clients | Development | All | 2 | 2 | Done | Clients asked for a new video recording of extension with voice | 0 | 0
All final document submission(23-02-2024) | Documentation | All | 12 | 10 | Done | Submission of final documents for R1 | 2 | 20
Updating Test plan tracker | Documentation | All | 3 | 3 | Done | Test plan tracker v2 | 0 | 0
Updating readme to give instructions | Documentation | All | 1 | 1 | Done | Updated readme for Steps of usage | 0 | 0
Week 10 (March 25 - March 31)
Updated Timeline submission to client | Documentation | All | 1 | 1 | Done | Submitted to client | 0 | 0
Exploring more on Digital Ocean Cloud | Development | All | 16 | 2 | Delayed | Client changed deployment mode | 14 | 700
Gmail working version to client | Development | All | 6 | 6 | Done | Given to client | 0 | 0
Week 11 (April 1 - April 7)
Fix meeting with client(1-04-2024) | Coordination | All | 2 | 2 | Done | Discussed problems in working of extension on gmail | 0 | 0
Thin text appearing on gmail | Development | Shreyansh, Siddharth | 10 | 10 | Done | Thintext was finally displayed by placing a div on the page with high z-index | 0 | 0
Thin text not being displayed at right of page | Development | Shreyansh | 5 | 5 | Done | Thin-text now doesnt overflow window in case of input/text-area | 0 | 0
Fix meeting with client(7-04-2024) | Coordination | All | 2 | 2 | Done | Backend introduction | 0 | 0
Fixed copy-pasting problem in gmail | Development | Shreyansh | 3 | 3 | Done | Removed <br> tag which formed on copy-pasting in gmail body | 0 | 0
Week 11 (April 8 - April 14)
Main Menu-extension integration | Development | Garvit | 5 | 5 | Done | Working of main menu buttons | 0 | 0
Extension deployment on backend Ubuntu server | Development | Shreyansh | 4 | 4 | Done | In coordination with dharmik, extension deployed | 0 | 0
Working of extension on Slack | Development | Shreyansh, Siddharth | 3 | 3 | Done | <p> tags within divs handled | 0 | 0
Working of extension on Whatsapp | Development | Shreyansh | 2 | 2 | Done | extension worlks on whatsapp | 0 | 0
shift-enter working now | Development | Shreyansh | 2 | 2 | Done | Shifting of caret fixed upon shift+enter | 0 | 0
Fix meeting with Client(10-04-2024) | Coordination | All | 4 | 4 | Done | Adding wait/ready button, updating thintext on hover | 0 | 0
synchronously wait for backend response | Development | Shreyansh | 3 | 3 | Done | model synchronously waits no longer giving previous outputs | 0 | 0
Caret between text doesnt cause problem | Development | Shreyansh | 1 | 1 | Done | problem fixed | 0 | 0
Fix meeting with Client(12-04-2024) | Coordination | All | 2 | 2 | Done | Discussion on bringing loader, backend logging of options | 0 | 0
Extension Menu buttons integration | Development | Priet,Garvit | 3 | 3 | Done | Buttons done, now just enable/disable on backend | 0 | 0
StatusTracker, MoM for meeting on 12-04 | Documentation | Priet,Garvit | 1 | 1 | Done | Adding current progress and meeting MoM | 0 | 0
Red/Green Dot on waiting/ready | Development | Priet | 3 | 2 | Done | Showing indicator on input box | 1 | 50
Storing extension settings on different websites | Development | Garvit | 4 | 0 | Delayed | Started handling no. of predictions setting in main menu | 4
Logging the predictions selected by user | Development | Siddharth | 3 | 3 | Done | The selected predictions will be logged to some file/database | 0 | 0
Week 11 (April 15 - April 21)
Fix meeting with Client(15-04-2024) | Coordination | All | 3 | 3 | Done | To check the progress and discuss about documentation
No. of predictions setting on main menu | Development | Garvit, Priet | 4 | 4.5 | Done | User should be able to select the no. of predictions he wants
Fix meeting with Client(18-04-2024) | Coordination | All | 3 | 3 | Done | Just a catch up meet
SSH Certificate for requests | Development | Shreyansh, Siddharth | 10 | 12 | Delayed | Not possible
Documentation of code and how to install extension | Documentation | All | 30 | 30 | Done | Documentation of code and it's fuctions along with documentation of installation of extension
Adding Function Docs in content.js | Development | Priet | 2 | 2 | Done | Added function defs inputs outputs to the code
Creating TestPlan Tracker v3 | Documentation | Priet | 3 | 3 | Done | Adding new functionalities implemented after R1 and their tests
Modifying other Docs like SRS, ProjectPlan based on progess and refinements after R1 | Documentation | Priet | 3 | 3 | Done | To update the extra functionalities and client changes in the Docs